## Slide 1: ITU-T SG12 Q19 Interim Meeting Objective and subjective methods for evaluating perceptual audiovisual quality in multimedia and television services
December 19, 2023
Online

## Slide 2
Agenda
Work item J.noref
Work item P.obj-recog
AOB

## Slide 3
Work item J.noref

## Slide 4
No reference method
ITU and VQEG had made several attempts for no-reference video quality measurement methods, but failed to produce Recommendations.
Recently, some promising results based on deep-learning methods have been reported.
Q19 has a work item J.noref for no-reference video quality measurement methods.
For the testplan of NR methods, we may use a VQEG testplan (e.g, HDTV project) as base text.
Without any requirements on PVSs and bitstream data, no reference methods can be easily evaluated.

## Slide 5
Main Issues
video resolutions and display types
codec types & bitrates
transmission errors
model evaluation
source video & data publication (release of subjective data, objective data)
PVS duration
proponents & ILG
subjective test method
performing subjective tests
schedule

## Slide 6
Resolution
UHD (2160p), FHD (1080p), HD (720p) and lower.
Each resolution may require a certain number test sets.
Considering limited resources, we may consider selecting one or two resolutions.
Decision: FHD only (horizontal/vertical)
Display
UHD TV, FHD TV, PC monitors, tablet, smart phone.
Each display may require a certain number test sets.
Considering limited resources, we may consider selecting one two display types.
Decision: TV monitors, PC monitors, mobile display

## Slide 7
Proponents & ILG
Tentative proponents:
  NTIA
  Yonsei
  VQEG member
  TU Ilmenau
  UVQ
Tentative ILG:
  Rise
  AGH

## Slide 8
Performing test design and subjective tests
Option 1: After model submission, proponents can perform test design (codec, bitrate, SRC, etc.), generate test data and conduct subjective tests.
Option 2: After model submission, ILGs can perform test design (codec, bitrate, SRC, etc.), and proponents generate test data and conduct subjective tests.
TBD

## Slide 9
Release of Subjective Data, Objective Data, and the Official Data Analysis
Option 1: Anyone can use them (public domain) - preferred
Option 2: Proponents and ILG can use them.
Option 3: Proponents can use them.
Preference for SRC: Use public source video sequences if possible.

## Slide 10
PVS duration
5, 8, 10, 12 sec
Proposal: 5s (no transmission errors), 8s (transmission errors allowed)
Decision: 5 sec (no transmission errors)
  Constant quality recommended.
  No artificial impairments.
  No scene cut.

## Slide 11
Codec and bitrates
DECISIONS
Codec: H.264, H.265, VP9, AV1, VVC.
Camera impairments (live capture) are allowed.
Bitrates (FHD)
  1080p SRC: 0.1–30 Mbps

## Slide 12
Transmission Error
Option 1: Compression only
Option 2: Allow Freeze (up to ??30%).
Decision: no transmission errors.

## Slide 13
Subjective Test Method
Decision: ACR.
TBD: Requirements on PVSs
  Repeating the same SRC

## Slide 14
Model Evaluation
Metric: RMSE, Pearson.
TBD

## Slide 15
Model Types in Recommendations
One model for all resolutions
Each model for target resolution
Decision: A model should handle horizontal/vertical FHD.

## Slide 16
Schedule
Finalization of test plan: June, 2024
Model submission: +6 months after testplan finalization
Test design +7 months after testplan finalization
Test PVS generation & +9 months after testplan finalization subjective tests
Objective data submission +11 months after testplan finalization
Final Report +12 months after testplan finalization

## Slide 17: THE END